## msplposites
circle | customer | site_type | site_id | tech | sub_tech | band | tech_quantity | activity | site_alocation_date | site_done_date | dtname | site_status | ohs_done_date | vendor_name | po_number | percentage_po | po_value | vendor_po | vendor_po no | report_submission_date | report_acceptance_date | upload_report | wcc_raise_date | wcc_receive_date | wcc_status | grn_raise_date | grn_receive_date | grn_status | invoice_date | payment_receive_date | Item | work_description | site_name
KK | Ericsson_BH | CAT | MYE320 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE296 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE333 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE188 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE035 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE314 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE289 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE306 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE003 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE069 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE298 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE322 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE575 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE055 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE670 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE155 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE300 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE274 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE032 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE331 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE019 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE385 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE088 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE145 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE028 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE096 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE267 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE596 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE166 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE426 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE010 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE029 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE080 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE275 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE524 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | CKKLI1 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | VAJAM3 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | VAJAM4 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE754 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE390 | 4G | FDD | L2100 | 1 | CAT | 2024-04-06 | 2024-07-06 | Anurag | done | 2024-07-06 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW
KK | Ericsson_BH | CAT | MYE099 | 4G | FDD | L2100 | 1 | CAT | 2024-06-28 | 2024-06-29 | Anurag | done | 2024-06-29 | MSPL | 4530261808 | 80% | 6200 | 4960 |  | 2024-07-09 | 2024-07-12 | done | 2024-07-12 | 2024-07-13 | done | 2024-07-13 |  | pending |  |  | 10 | GNA234393/NT/CAT LTE T/FDD+VOLTE DRIVE WITH AZQ_NEW